## Project Plan & Timeline
Purpose | This document describes the project tasks, deadlines and task owners
Team | DS 1
Submission Date | 2026-03-01
| # |  | Task | Owner | Git Reviewer | Due Date | Review Due Date | Submission Date | Comments
| 1 | - | Project Planning
| 1 | - | Create Readme & Submit | Baruni | All | 2026-02-27 | 2026-02-28 | 2026-03-01
| 2 | - | Create project plan & submit | Baruni | All | 2026-02-27 | 2026-02-28 | 2026-03-01
| 3 | - | Exploratory Data Analysis
| 3 | a | Missing Value Imputation + Visuals (if applicable) | Baruni | Puru | 2026-03-02 | 2026-03-03 | 2025-03-07
| 3 | b | Duplicate Data Inspection + Visuals (if applicable) | Haroon | Baruni | 2026-02-28 | 2026-03-01 | 2025-03-07
| 3 | c | Feature Correlation Analysis + Visuals (if applicable) | Haroon | Raghav | 2026-02-28 | 2026-03-01 | 2025-03-07
| 3 | d | Data Scaling + Visuals (if applicable) | Raghav | Haroon | 2026-02-28 | 2026-03-01 | 2025-03-07
| 3 | e | Data Encoding+ Visuals (if applicable) | Raghav | Baruni | 2026-03-02 | 2026-03-03 | 2025-03-07
| 4 | - | Model Creation
| 4 | a.1 | KNN Model Creation + Pipeline | Puru | Baruni | 2026-03-02 | 2026-03-03 | 2025-03-07 | Create in independent notebooks and we will later merge. Create your own folder and put your notebook in it. Prevents conflicts. Will merge to a main notebook at the end.
| 4 | a.2 | KNN Model Evaluation Metrics | Puru | Baruni | 2026-03-02 | 2026-03-03 | 2025-03-07 | 2 or 3 metrics on efficiency/accuracy per model
| 4 | a.3 | KNN Model Observations Summary | Puru | Baruni | 2026-03-02 | 2026-03-03 | 2025-03-07
| 4 | a.4 | KNN Model Visuals | Puru | Baruni | 2026-03-02 | 2026-03-03 | 2025-03-07
| 4 | b.1 | Logistic Regression Model (Binary Classification) Creation + Pipeline | Raghav | Puru | 2026-03-02 | 2026-03-03 | 2025-03-07
| 4 | b.2 | Logistic Regression Model (Binary Classification) Evaluation Metrics | Raghav | Puru | 2026-03-02 | 2026-03-03 | 2025-03-07
| 4 | b.3 | Logistic Regression Model (Binary Classification) Observations Summary | Raghav | Puru | 2026-03-02 | 2026-03-03 | 2025-03-07
| 4 | b.4 | Logistic Regression Model (Binary Classification) Visuals | Raghav | Puru | 2026-03-02 | 2026-03-03 | 2025-03-07
| 4 | c.1 | Naïve baye based theorem Creation + Pipeline | Haroon | Raghav | 2026-03-02 | 2026-03-03 | 2025-03-07
| 4 | c.2 | Naïve baye based theorem Evaluation Metrics | Haroon | Raghav | 2026-03-02 | 2026-03-03 | 2025-03-07
| 4 | c.3 | Naïve baye based theorem Observation Summary | Haroon | Raghav | 2026-03-02 | 2026-03-03 | 2025-03-07
| 4 | c.4 | Naïve baye based theorem Visuals | Haroon | Raghav | 2026-03-02 | 2026-03-03 | 2025-03-07
| 5 | - | Reporting
| 5 | a | Code Merge/finalization | All | All | 2026-03-04 | N/A | 2025-03-07
| 5 | b | Final test run on reproducability | All | All | 2026-03-04 | N/A | 2025-03-07
| 5 | c | Consensus on observations/Summary | All | All | 2026-03-04 | N/A | 2025-03-07
| 5 | d | Update README | All | All | 2026-03-05 | N/A | 2025-03-07
| 5 | e | Create Presentation | Baruni | All | 2026-03-05 | 2026-03-06 | 2025-03-07
| 5 | f | Practice Presentation - Speakers | All | All | 2026-03-06 | N/A | 2025-03-07
| 5 | g | Final Presentation | All | All | 2025-03-07 | N/A | 2025-03-07

## Code Checklist
Purpose | For each model, data cleansing task confirm the following objectives have been met
Item | Task | Missing Value Imputation + Visuals (if applicable) | Duplicate Data Inspection + Visuals (if applicable) | Feature Correlation Analysis | Data Scaling | Data Encoding | KNN | Logical Regression | Naïve Bayes
1 | 1 Visual (at minimum for models, only if applicable for data cleansing task) - accessible, inclusive, diverse - suitable for the message/audience - accurate and does not misrepresent the data
2 | Model README file that's linked to the main README
3 | Code - Well written comments - Structured code/easy to read and follow - reproducible
4 | Observations Summarized - 1-3 key insights - business recommendations quantified
5 | Produces the same results once all code is merged